## Draw Check list
First Draw
NLB (No Loan Balance) or Cap Partner aka Sold loan | Loan Buyer or Capital Partner in SF
Servicer Payment due (Check Loan agreement for due date) Loans that close after 7/1/2025 should have a payment due date of the first of the month. Loans closed prior to that date have a payment due date of the 10th | Jonathan we can review the loan agreements, please just populate with next due date
Check FCI to see if borrowing entity is late for any other payments
Maturity | SF - Current Maturity Date
Taxes Not Delinquient | Pull from ICE report in Teams
Workday Vendor Set Up | Pull in supplier code
Property Insurance Current | Pull from OSC report
W-9
Wire Form
Permits - Structural
LW on all projects Budgets >=150k
LW on all projects Draws >=25k
LW on all line item draws >=7500
POP & Invoices soft cost & non inspectable items(for example Construction Staking, Septic work, etc.) (up to 6 months prior to the loan close date.)
Title Required CH & Toorak
Invoices sent to Accounting to pay title
Send Approved draw to borrower for esignature
GUC Checklist
GC License https://www.procore.com/library/contractors-license-guide-all-states#georgia
GC Contract
All building & MEP Permit
Lien waiver for all draws
Project Schedule
ALL MEP Permits. Need contract if borrower is GC
Retainage - Follow Loan Agreement (if we have l lender discretion we will NOT hold retainage until final draw)
Builders Risk Insurance
GC Consent
Architect Consent
Engineer Consent
check remaining value in sf
Note on A2: Melanie Cave: Look inside the advance under Capital Partner if this field is blank put N/A
Note on A6: Melanie Cave: Look at ICE report in Teams/Channels/Asset Management/Collaboration/Files/ICE updated Tax
Note on A8: Melanie Cave: Check Monthly Report. If force placed insurance is in place, get updated insurance send to bruce & upload to box and sf insdocs8121@oscis.com and Bruce Young <byoung@rossdiv.com>
Note on A16: Melanie Cave: Toorak Requires Title when funding accumulated fund => $75k; Churchill Requires Title when funding accumulated fund => $210K Send title request to title customerservice@singlesourceproperty.com; Send escalations to Chris Porto cporto@singlesourceproperty.com Please provide a title date down endorsement good through DD/MM/YY in the amount of $$$$(total fundings to date including interest, initial advance and construction advances). Provide them with the Borrowing entity: and Asset Address:
Note on A28: Melanie Cave: Check Monthly Report. If force placed insurance is in place, get updated insurance send to bruce & upload to box and sf insdocs8121@oscis.com and Bruce Young <byoung@rossdiv.com>